## Instructions
ARTC HUNTER VALLEY INTEGRATED PLAN TEMPLATE
Version | 2.1 | OPE-FM-047
Date | 2022-12-21
Authored | F Wilson
Reviewed | A Kennedy
Authorised | B Morris
Document Owner | Manager Hunter Valley Network Integration. The Integrated Scheduling Manager shall be the point of contact for enquiries relating to this template.
Document Ref# | OPE-PR-041
Reference Documents
OPE-PR-041 Weekly Integrated Network Planning Process v2.1
OPE-PR-038 Unplanned Track Possession Request Procedure
Instructions: | Using the template are located on the WIP tab - additional rows may be added by duplicating the existing rows should you need more than 5 requests. Five examples have been provided.
Additional Notes: | For any additional jobs, cancellations and alterations please submit to the following in their respective timelines;
| HVIntegration@artc.com.au | for the following weeks plan – until 1400 hours on Tuesday each week for the following week's plan. Late jobs will only be accepted until 1200 hours on Thursday each week for the following week’s plan with this address. Future works that are in Weekly Plans further out can also be sent to this address.
| IProcessCoordinator@artc.com.au | for changes or additional jobs or cancellations within the current week's plan but not the live day plan – from 1200 hours each Friday once the WIP has been published until 1500 hours each day prior to DIP publication.
For changes or additional jobs within the live daily plan please contact the Network Control Board for that area.

## WIP
WEEKLY INTEGRATED PLAN - JOB TEMPLATE
WORK GROUP | BOARD | PRIORITY | LINE | LOCATION FROM | KM FROM | PROTECTING PTS OR SIGNAL | LOCATION TO | KM TO | PROTECTING PTS OR SIGNAL | WORK ON TRACK AUTHORITY | WORK ORDER NUMBER | DATE RANGE TO COMPLETE THE WORK | ASSIGNED DATE | GENERAL SCOPE DESCRIPTION | TOTAL TIME REQUIRED | TIME BLOCKS REQUIRED | TIME CONSTRAINTS | TIME IDENTIFIED | ADJACENT LINE PROTECTION | COMMENTS | ARTC CONTACT | SUPERVISOR NAME & CONTACT | PO NAME & NUMBER
EXE | WEST, NWest |  | Single Main | Dubbo | 493 |  | Dubbo West | 494 |  | TOA |  | 01/01/2023-06/01/2023 | 2023-01-05 | Test Example | 120 | 2 x 60 | 0600-1700
EXE | LH |  | Up & Down North Coast | Maitland | 193 |  | Telarah | 194 |  | TOA |  |  | 2023-01-06 | Test Example | 120 | 2 x 60
EXE | LH |  | Up & Down North Coast | Maitland | 193 |  | Telarah | 194 |  | TOA |  |  | 2023-01-07 | Test Example | 120 | 2 x 60
EXE | LH |  | Up & Down North Coast | Maitland | 193 |  | Telarah | 194 |  | TOA |  |  | 2023-01-08 | Test Example | 120 | 2 x 60
EXE | LH |  | Up & Down North Coast | Maitland | 173 |  | Telarah | 194 |  | ASB |  |  | 2023-01-09 | Test Example | 120 | 2 x 60
Drop Down | Auto Generated | Not mandatory. Live Run to use in DoO. | Not Mandatory for WIC. All other authorities mandatory. Drop Down Option for Free Text | Drop Down | KM Value enforced | Not mandatory. Required for Possessions. | Drop Down | KM Value enforced | Not mandatory. Required for Possessions. | Drop Down | HV Assets Use Only | Date range for when the work can start and when it must be finished by | Date enforced: Must be after today's date. | Free Text | Numerical Value enforced >0 Can be blank for WIC/LOW | Free Text | Free Text | Not mandatory. Required for Possessions. | Free Text. Include detail of which line is required and how long for. | Free Text | For 3rd party or contract works Free Text | Free Text | Free Text
Legend:
Mandatory information
Non-mandatory information

## tbl_refTracks (hidden)
lineName
1 Arrival Road
1 Departure Road
1 Road 9 Nest
1 Storage Road
10 Departure Road
2 Arrival Road
2 Departure Road
2 Road 9 Nest
2 Storage Road
3 Arrival Road
3 Departure Road
3 Road 9 Nest
3 Storage Road
4 Departure Road
4 Road 9 Nest
5 Departure Road
5 Road 9 Nest
6 Departure Road
6 Road 9 Nest
7 Departure Road
8 Departure Road
9 Departure Road
Arrival & Departure Roads
Arrival Road
Brambles Loop
Bullock Island Balloon Loop
Bullock Island Shunting Neck
By Pass Road
Coal Siding Road
Compound Road
Departure Road
Down Coal Road
Down Coal/Down Main
Down Islington Loop
Down Kooragang Branch
Down Local Road
Down Loop
Down Main
Down North Coast
Down North Fork
Down Relief
Down South Fork
Down Whittingham Branch
Islington Arrival Road
J Frame Loop
Loop
Loop to Reception Sidings Road
Main Arrival Road
Main Line and Loops
Morandoo Loop
Nine Nest Loop
No3 Arrival Road
No1 Bullock Island Arrival Road
No1 Bullock Island Coal Arrival Road
No1 Coal Arrival Road
No1 Departure Road
No1 East End Road
No1 Grain Arrival Road
No1 Grain siding
No1 Islington Departure Road
No1 Reception siding
No1 Road Morandoo
No10 Road Morandoo
No11 Road Morandoo
No12 Road Morandoo
No13 Road Morandoo
No2 Bullock Island Arrival Road
No2 Bullock Island Coal Arrival Road
No2 Coal Arrival Road
No2 Departure Road
No2 East End Road
No2 Grain Arrival Road
No2 Grain siding
No2 Islington Departure Road
No2 Reception siding
No2 Road Morandoo
No3 Coal Arrival Road
No3 East End Road
No3 Grain siding
No3 Reception siding
No3 Road Morandoo
No4 East End Road
No4 Grain siding
No4 Reception siding
No4 Road Morandoo
No5 East End Road
No5 Grain siding
No5 Reception siding
No5 Road Morandoo
No6 Grain siding
No6 Road Morandoo
No7 Road Morandoo
No8 Road Morandoo
No9 Road Morandoo
North West Loop Line
Silo Arrival Road
Single Main
Single Whittingham Branch
Up & Down & Single Whittingham Branch
Up & Down Coal Road
Up & Down Coals - Arrival & Departure Roads
Up & Down Kooragang Branch
Up & Down Local Roads
Up & Down Local Roads - Triangle Loop - Up & Down Mains
Up & Down Local Roads - Triangle Loop - Up & Down Mains - Single Mains - Loops
Up & Down Main
Up & Down Main - Up & Down South Fork
Up & Down Mains - Up & Down North Coast - Up & Down Locals - Up & Down South Forks
Up & Down North Coast
Up & Down North Fork
Up & Down North/South Fork - Up & Down Kooragang Branch
Up & Down South Fork
Up Coal Road
Up Coal Road & Down Main
Up Islington Loop
Up Kooragang Branch
Up Local Road
Up Loop
Up Main
Up Main/Up Coal Road
Up North Coast
Up North Fork
Up Relief
Up South Fork
Up Whittingham Branch
Wagon Arrival Road
Wagon Repair Road
Walsh Point Line
Waratah Arrival Road
Waratah Departure Road
Weighbridge Road
Hexham Relief Roads

## tbl_refLocationControl (hidden)
locationCode | locationControlBoard
ACS | UH1
ADN | UH2
ADQ | UH2
AGK | HVTOCO
AGR | HVTOCO
ALC | HVTOCO
ALD | MH
ARD | UH2
ATC | UH1
ATN | UH1
BAA | North
BAE | UH3
BBS | North
BCI | PTW
BCL | MH
BCT | PTW
BEG | UH2
BEL | MH
BFD | UH2
BGI | NON-OP
BIP | PTW
BJA | UH1
BJC | UH1
BJE | North
BJL | UH1
BKI | PTW
BLM | LH
BLR | HVTOCO
BLT | HVTOCO
BNA | HVTOCO
BNX | MH
BOG | North
BRA | UH2
BRW | HVTOCO
BSF | LH
BUR | North
BYL | UH3
BZA | North
CAM | MH
CGC | UH3
CKI | UH2
CLS | North
CMJ | UH1
CMR | HVTOCO
DBO | HVTOCO
DEN | UH3
DRJ | UH1
DRY | UH1
EGN | LH
EHI | North
EMD | LH
EWB | HVTOCO
FAR | LH
FTR | LH
GBJ | HVTOCO
GCJ | North
GDC | North
GDH | North
GDX | North
GLG | HVTOCO
GNM | HVTOCO
GTA | MH
GTR | UH1
HBJ | PTW
HVY | UH1
HVZ | UH1
HXM | LH
KBY | UH1
KCU | KCL
KDR | KCL
KEJ | KCL
KGV | KCL
KNF | KCL
KNK | UH2
KRB | UH3
KSF | KCL
KYP | KCL
LDL | UH1
LOC | LH
MBH | MH
MDI | UH2
MDO | PTW
MET | LH
MLD | LH
MLJ | UH3
MLR | UH3
MMK | UH3
MMO | UH3
MMT | UH3
MOC | UH1
MOR | HVTOCO
MOY | HVTOCO
MRE | HVTOCO
MRG | HVTOCO
MRL | UH2
MSS | HVTOCO
MTB | UH1
MTW | UH1
MUS | UH1
MUU | UH3
MWS | HVTOCO
NBI | North
NBJ | North
NCA | KCL
NCD | KCL
NCJ | North
NCL | North
NCU | KCL
NDC | UH1
NDJ | UH1
NLX | HVTOCO
NMN | HVTOCO
NNW | HVTOCO
NTS | HVTOCO
PAJ | UH1
PCA | PTW
PGR | UH2
PKH | HVTOCO
PRE | North
PVL | UH2
QDI | UH2
QDW | UH2
QUI | UH2
RTH | MH
SAN | LH
SCH | PTW
SCN | UH2
SGL | MH
SLR | UH1
SOL | UH3
SPR | HVTOCO
STC | Coast A
STF | Coast A
SXJ | MH
TGR | UH2
TLH | LH
TMR | HVTOCO
TON | LH
TRJ | HVTOCO
TRO | LH
TWN | North
ULN | UH3
WAK | North
WCK | North
WCK | UH2
WCP | North
WCW | North
WHM | MH
WIP | UH3
WJJ | UH3
WJL | UH3
WKC | North
WRK | PTW
WSH | PTW
WTE | UH2
WTH | PTW
WTL | HVTOCO
XYZ | PTW
YAW | UH3

## tbl_refLocations (hidden)
locationName | tbl_refLocationControl.locationControlBoard | locationZone
Aberdeen | UH2 | 3
Alectown West | NWest | CNW
Allandale | MH | 1
Antiene | UH1 | 1
Antiene Coal Unloader | UH1 | 1
Ardglen | UH2 | 3
Ardglen Quarry | UH2 | 3
Ashton Coal | UH1 | 1
Baan Baa | North | 3
Baerami | UH3 | 2
Ballimore | WEST | CNW
Belford | LH | 1
Bellata | NWest | CNW
Bells Gate | UH2 | 3
Bengalla | UH1 | 1
Bengalla Colliery | UH1 | 1
Beni | WEST | CNW
Beresfield | LH | 1
Binnaway | WEST | CNW
Birriwa | WEST | CNW
Blandford | UH2 | 3
Bloomfield Colliery | LH | 1
Bobbiwaa | NWest | CNW
Boggabri | North | 3
Boggabri Coal | North | 3
Bomera | WEST | CNW
Braefield | UH2 | 3
Branxton | MH | 1
Breeza | North | 3
Bulga Coal | MH | 1
Bullock Island Yard | PW | 1
Burilda | North | 3
Bylong | UH3 | 2
Camberwell Coal Loader | MH | 1
Camberwell Junction | UH1 | 1
Camurra | NWest | CNW
Caroona | WEST | CNW
Chilcotts Creek | UH2 | 3
Coggan Creek | UH3 | 2
Connemarra | WEST | CNW
Crooble | NWest | CNW
Croppa Creek | NWest | CNW
Curlewis | North | 3
Daisymede Junction | north | 3
Dartbrook Junction | UH1 | 1
Denman | UH3 | 2
Drayton Coal Loader | UH1 | 1
Drayton Junction | UH1 | 1
Dubbo | WEST | CNW
Dubbo East Junction | WEST | CNW
Dubbo Fletchers | WEST | CNW
Dubbo West | NWest | CNW
Dunedoo | WEST | CNW
East Greta Junction | LH | 1
East Maitland | LH | 1
Edgeroi | NWest | CNW
Elong Elong | WEST | CNW
Emerald Hill | North | 3
Farley | LH | 1
Farley Triangle | LH | 1
Gap Junction | NORTH | 3
Goninans Siding | PW | 1
Goobang Junction | NWest | CNW
Goobang North | NWest | CNW
Goonumbla | NWest | CNW
Grasstree | UH1 | 1
Greta | MH | 1
Greta TSF | MH | 1
Gulgong | WEST | CNW
Gulgong North | WEST | CNW
Gunnedah | North | 3
Gunnedah Colliery | North | 3
Gurley | NWest | CNW
Hanbury Junction | PW | 1
Hexham | LH | 1
Hexham Aurizon | LH | 1
Hexham East | LH | 1
Hexham West | LH | 1
High Street | LH | 1
Hunter Valley 1 Coal Loader | UH1 | 1
Hunter Valley 2 Coal Loader | UH1 | 1
Islington Junction | PW | 1
Kankool | UH2 | 3
Kerrabee | UH3 | 2
Koolbury | UH1 | 3
Kooragang | KCL | 1
Kooragang Island | KCL | 1
Kooragang North Fork | KCL | 1
Liamena | WEST | CNW
Liddell | UH1 | 1
Liddell Coal Loader | UH1 | 1
Lochinvar | MH | 1
Maitland | LH | 1
Mangoola | UH3 | 2
Mangoola Loop | UH3 | 2
Mangoola Mine | UH3 | 2
Mangoola Mine Junction | UH3 | 2
Maules Creek | north | 3
Mendooran | WEST | CNW
Merrygoen | WEST | CNW
Metford | LH | 1
Mickibri | NWest | CNW
Milguy | NWest | CNW
MINDARIBBA | Coast A | 1
Minimbah | MH | 1
Minore | NWest | CNW
Moolarben | UH3 | 2
Moolarben Junction | UH3 | 2
Morandoo | PW | 1
Moree | NWest | CNW
Moree East | NWest | CNW
Moree South | NWest | CNW
Mt Arthur | UH1 | 1
Mt Owen | UH1 | 1
Mt Owen Coal Loader | UH1 | 1
Mt Pleasant | UH1 | 1
Mt Thorley | MH | 1
Murgo | HVTOCO | CNW
Muronbung | WEST | CNW
Murrumbo | UH3 | 2
Murrurundi | UH2 | 3
Murulla | UH2 | 3
Muswellbrook | UH1 | 1
Nanardine | NWest | CNW
Narrabri | NWest | CNW
Narrabri Coal | North | 3
Narrabri Coal Junction | North | 3
Narrabri Coal Loader | NORTH | 3
Narrabri Junction | NWest | CNW
Narrabri North | NWest | CNW
Narromine | NWest | CNW
Narromine Agrigrain | NWest | CNW
Narromine South | NWest | CNW
Narromine South West | NWest | CNW
Narwonah | NWest | CNW
Narwonah Awb | NWest | CNW
NCIG | KCL | 1
Neilrex | WEST | CNW
Newdell Coal Loop | UH1 | 1
Newdell Junction | UH1 | 1
North Star | NWest | CNW
Nundah | UH1 | 1
Pages River | UH2 | 1
Parkville | UH2 | 3
Peak Hill | NWest | CNW
Penneys Rd | NWest | CNW
Pennys Road | NWest | CNW
Piambra | WEST | CNW
Port Waratah | PW | 1
Premer | WEST | CNW
Puggoon | WEST | CNW
Quipolly | UH2 | 3
Quirindi | UH2 | 3
Quirindi Wheat Siding | UH2 | 3
RAVENSWORTH JUNCTION | UH1 | 1
Ravensworth Washery Loop | UH1 | 1
Rixs Creek Coal Loader | UH1 | 1
Sandgate | LH | 1
Sandy Hollow | UH3 | 2
Saxonvale Junction | MH | 1
Scholey Street | PW | 1
Scone | UH2 | 3
Singleton | MH | 1
Springridge | WEST | CNW
St Heliers | UH1 | 1
STRATFORD JUNCTION | Coast A | 1
Tamarang | WEST | CNW
Tarro | LH | 1
Telarah | LH | 1
Thornton | LH | 1
Tikitere | HVTOCO | CNW
Timjelly | NWest | CNW
Togar | UH2 | 3
Tomingley West | NWest | CNW
Troy Junction | WEST | CNW
Turrawan | North | CNW
Tycannah Creek | NWest | CNW
Ulan | UH3 | 2
Ulan Colliery | UH3 | 2
Victoria Street | LH | 1
Walsh Point | KCL | 1
Wambo | MH | 1
WARABROOK | PW | 1
WARATAH | PW | 1
Waterloo Creek | NWest | CNW
Watermark | North | 3
Weetaliba | WEST | CNW
Werris Creek | North | 3
Werris Creek Coal Siding | North | 3
Werris Creek Grain Terminal | North | 3
Whittingham | MH | 1
Willow Tree | UH2 | 3
Wilpinjong | UH3 | 2
Wilpinjong Coal Loader | UH3 | 2
Wingen | UH2 | 3
Wollar | UH3 | 2
Wyanga | NWest | CNW
Yannergee | WEST | CNW
Yarrawa | UH3 | 2

## tbl_wotMethods (hidden)
wotCode
ANWT300
WIC
LOW
ASB
TOA
LPA
TWA

## tbl_teamCodes (hidden)
TeamCode | BU_Code | Team Description
APP | NI | Annual Possession Plan
BCD | CW | Corridor Works - Ballast Cleaning and Drainage
BIN | CNW | Binnaway PC
CD | AP | Asset Planning - Closedown Team
COM | CORP | Corporate Communications
CRN | OTH | Country Regional Network
CSS | CORP | Corporate Communications
DBO | CNW | Dubbo PC
DEV | PE | Plant & Engineering - Development
EXE | OTH | External Works - Open Access / Customers
EXT | PBD | Property & Business Development - ARTC External Works / 3rd Party
GDH | AP | Asset Planning - Gunnedah PC
INR | IR | Inland Rail
INT | CORP | Corporate Interface Management
MAM | OTH | Machine Maintenance
MBK | AP | Asset Planning - Muswellbrook PC
MLD | AP | Asset Planning - Maitland PC
NBI | CNW | Narrabri PC
OTH | OTH | Other ARTC
PER | CW | Corridor Works - Perway
PJT | CNW | CNW Projects
PKS | CNW | Parkes PC
PLT | PE | Plant & Engineering - ARTC Plant
PLT | PE | Heavy Plant Team - CNW
PTW | AP | Asset Planning - Port Waratah / Carrington PC
REL | PE | Plant & Engineering - Reliability
RRG | AP | Asset Planning - Resurfacing and Rail Grinding
RTH | MHV | Maintenance Hunter Valley - Rutherford PC
SIG | CW | Corridor Works - Signalling
SP | PE | Plant & Engineering - Engineering & Special Projects
STR | CW | Corridor Works - Structures
TAR | INTRST | Telarah to Acacia Ridge Corridor
TCS | CORP | Corporate Train Control Systems
TRAN | OTH | Transport NSW / Sydney Trains
TRG | CW | Corridor Works - Track Recons and Geotech
WAY | CORP | Corporate Wayside